## Hoja1
Fase de desarrollo	Tarea	Fecha Inicio	Fecha Fin	Horas de trabajo	Días
Fase 0	Instalar Webstorm	05/03/20	05/03/20	1	1
	Instalar node.js, Angular e Ionic	05/03/20	05/03/20	1	1
	Repasar HTML y CSS	06/03/20	06/03/20	3	1
	Aprendizaje de Typescript	07/03/20	09/03/20	4	3
	Aprendizaje básico de Angular	07/03/20	09/03/20	8	3
	Aprendizaje básico de Ionic	10/03/20	11/03/20	4	2
	Crear un componente básico usando Angular e Ionic	12/03/20	13/03/20	5	2
	Aprendizaje del uso de “pages”	14/03/20	14/03/20	2	1
	Crear de una aplicación simple con distintas “pages”	15/03/20	16/03/20	4	2
	Aprendizaje del uso de servicios Angular	17/03/20	17/03/20	3	1
	Aprendizaje del uso de directivas Angular	18/03/20	18/03/20	2	1
	Estudio de VIRTRA-EL	18/03/20	19/03/20	4	2
Fase 1	Diagramas del sistema	20/03/20	20/03/20	5	1
	Header component	21/03/20	22/03/20	6	2
	Footer component	23/03/20	24/03/20	4	2
	Home page	25/03/20	26/03/20	3	2
	Project page	25/03/20	26/03/20	1	2
	Members page	25/03/20	26/03/20	1	2
	Contact page	25/03/20	27/03/20	2	3
	Access page	25/03/20	28/03/20	2	4
	Register page	25/03/20	28/03/20	2	4
	Exercises page	25/03/20	28/03/20	2	4
	Session page	29/03/20	02/03/20	6	5
	UserHeaderMenu component	29/03/20	29/03/20	2	1
	Servicios Angular para ejercicios y sesiones	30/03/20	30/03/20	4	1
	Desarrollo del sistema factory	31/03/20	02/04/20	10	3
	Desarrollo del sistema subscription	31/03/20	02/04/20	6	3
	Assistant component	31/03/20	02/04/20	4	3
	Documentación sobre la implementación de ejercicios y sesiones	03/04/20	03/04/20	2	1
Fase 2	WordListExercise development	03/04/20	07/04/20	8	5
	LogicalSeriesExercise development	05/04/20	12/04/20	12	8
	SemanticSeriesExercise development	10/04/20	20/04/20	6	11
	PositionsExercise development	15/04/20	29/04/20	15	15
	DirectNumbersExercise development	30/04/20	04/05/20	14	5
	NumbersAndVowelsExercise development	05/05/20	05/05/20	4	1
	PyramidsExercise development	06/05/20	06/05/20	8	1
	WordListExerciseAlternative development	07/05/20	07/05/20	6	1
	MouseDialogExercise development	08/05/20	08/05/20	4	1
	IntroductionExercise, QuestionnaireExercise, FirstHelpExercise development	09/05/20	10/05/20	6	2
	SecondHelpExercise, InstrumentalQuestionnaireExercise development	11/05/20	13/05/20	3	3
	ClassifyObjectsExercise development	14/05/20	17/05/20	10	4
			Total horas:	199

	Tarea	Fecha Inicio	Días
	Fase 0	05/03/20	14
	Instalar Webstorm	05/03/20	1
	Instalar node.js, Angular e Ionic	05/03/20	1
	Repasar HTML y CSS	06/03/20	1
	Aprendizaje de Typescript	07/03/20	3
	Aprendizaje básico de Angular	07/03/20	3
	Aprendizaje básico de Ionic	10/03/20	2
	Crear un componente básico usando Angular e Ionic	12/03/20	2
	Aprendizaje del uso de “pages”	14/03/20	1
	Crear de una aplicación simple con distintas “pages”	15/03/20	2
	Aprendizaje del uso de servicios Angular	17/03/20	1
	Aprendizaje del uso de directivas Angular	18/03/20	1
	Fase 1	20/03/20	15
	Diagramas del sistema	20/03/20	1
	Header component	21/03/20	2
	Footer component	23/03/20	2
	Home page	25/03/20	2
	Project page	25/03/20	2
	Members page	25/03/20	2
	Contact page	25/03/20	3
	Access page	25/03/20	4
	Register page	25/03/20	4
	Exercises page	25/03/20	4
	Session page	29/03/20	5
	UserHeaderMenu component	29/03/20	1
	Servicios Angular para ejercicios y sesiones	30/03/20	1
	Desarrollo del sistema factory	31/03/20	3
	Desarrollo del sistema subscription	31/03/20	3
	Assistant component	31/03/20	3
	Documentación sobre la implementación de ejercicios y sesiones	03/04/20	1
	Fase 2	03/04/20	44
	WordListExercise development	03/04/20	5
	LogicalSeriesExercise development	05/04/20	8
	SemanticSeriesExercise development	10/04/20	11
	PositionsExercise development	15/04/20	15
	DirectNumbersExercise development	30/04/20	5
	NumbersAndVowelsExercise development	05/05/20	1
	PyramidsExercise development	06/05/20	1
	WordListExerciseAlternative development	07/05/20	1
	MouseDialogExercise development	08/05/20	1
	IntroductionExercise, QuestionnaireExercise, FirstHelpExercise development	09/05/20	2
	SecondHelpExercise, InstrumentalQuestionnaireExercise development	11/05/20	3
	ClassifyObjectsExercise development	14/05/20	4